## 6 months
Sample Event Timeline
| Event Planners |  |  | Event Date | Event Location
| Person 1 |  |  | 00/00/0000 | Event Location
Person 2
6 |  | Organize and discuss committee roles & responsibilities |  |  | Point Person:
MONTHS
|  | □ | Who are your key point people?
|  | □ | Schedule monthly check-in meetings
|  | Brainstorm and create an event management plan where you discuss the following: |  |  | Point Person:
|  | □ | Goals |  | □ | Budget
|  | □ | Potential Location |  | □ | Activities
|  | □ | Potential Event Dates |  | □ | Engagement Strategy
|  | □ | Attendence |  | □ | [Add your own]
|  | Tour potential venues and choose one |  |  | Point Person:
|  | □ | Are the necessary facilities and locations availalbe?
|  | □ | Is the venue within budget?
|  | □ | Will you need proof of insurance coverage?
|  | □ | Do you need WIFI and/or A/V availability?
|  | □ | Secure venue and have contract reviewed and signed by an advisor.
|  | Work with VPF and/or advisor to create a budget |  |  | Point Person:
|  | Consider sponsorship and in-kind donations, if needed? |  |  | Point Person:
|  | □ | Determine acquisition teams
|  | □ | Generate an acquisition "wish list"
|  | □ | Create sponsorship folders
|  | Send Save the Dates, if necessary |  |  | Point Person:

## 3 months
Sample Event Timeline
| Event Planners |  |  | Event Date | Event Location
| Person 1 |  |  | 00/00/0000 | Event Location
Person 2
3 |  | Confirm bookings of the following: |  |  | Point Person:
MONTHS
|  | □ | Photographer and/or videographers
|  | □ | Any equipment
|  | □ | Security
|  | □ | [Add your own]
|  | Marketing and publicity plan created |  |  | Point Person:
|  | □ | Print |  | □ | Blog
|  | □ | Campus media |  | □ | Social media
|  | □ | Email marketing |  | □ | Press release
|  | □ | Website/Facebook page live |  | □ | [Add your own]
|  | Confirm the key roles & responsibilities of the committees and circulate this information |  |  | Point Person:
|  | Publicize & invite |  |  | Point Person:
|  | □ | Obtain address/emails for invitee list
|  | □ | Design print and electronic invitations (need advisor apporval)
|  | □ | Ensure that you have a site or webpage to send invitees to where they can purchase tickets, sign up and/or make a donation
|  | □ | Send notes to chapter and local alumnae to invite them to the event and solicit donations
|  | Get all members invovled |  |  | Point Person:
|  | □ | Educate chapter about the event (goals, how to talk the event, roles, etc.)
|  | □ | Have each chapter member sign up for a committee
|  | Complete the Event Planner Form on your Officer Portal |  |  | Point Person:
|  | Submit your event to the Foundation |  |  | Point Person:
|  | □ | Visit www.alphaphifoundation.org/events and submit your event |  |  | Click Here

## 6 weeks
Sample Event Timeline
| Event Planners |  |  | Event Date | Event Location
| Person 1 |  |  | 00/00/0000 | Event Location
Person 2
6 |  | Review, Edit & Check |  |  | Point Person:
WEEKS
|  | □ | Event Management Plan
|  | □ | Site Plan
|  | □ | Plans for booths and activities and any utility requirements (access to electricity, water, etc.)
|  | □ | [Insert other responsibility]
|  | Marketing |  |  | Point Person:
|  | □ | Finalize and implement communications plan
|  | □ | Design and print any flyers, posters, programs, etc.
|  | □ | Change your profile pictures
|  | □ | [Insert other responsibility]
|  | If necessary, request for a Certificate of Insurance |  |  | Point Person:
|  | Create a day-of event agenda |  |  | Point Person:

## 4 weeks
Sample Event Timeline
| Event Planners |  |  | Event Date | Event Location
| Person 1 |  |  | 00/00/0000 | Event Location
Person 2
|  | Review and finalize |  |  | Point Person:
WEEKS
|  | □ | Event Management Plan |  | □ | Security
|  | □ | Committee and member responsibilities |  | □ | Gifts and giveaways
|  | □ | Insurance |  | □ | Data entry/check out committee determines proper procedure
|  | □ | Equipment and WIFI capabilities |  | □ | [Add your own]
|  | Create post-event engagement plan (thank you cards, social media posts, etc.) |  |  | Point Person:
|  | Organize day-of teams for the event, if needed |  |  | Point Person:
|  | □ | Set-up and clean-up crew |  | □ | Operations crew
|  | □ | Entertainment |  | □ | [Add your own]
|  | Share the donation page with your target audience |  |  | Point Person:
|  | □ | Share the chapter donation link with your attendees |  |  | Chapter Donations
|  | Marketing blitz begins |  |  | Point Person:
|  | □ | Press release sent |  | □ | Operations crew
|  | □ | Social media plan in swing |  | □ | [Add your own]

## 1 week
Sample Event Timeline
| Event Planners |  |  | Event Date | Event Location
| Person 1 |  |  | 00/00/0000 | Event Location
Person 2
1 |  | Host a pre-event briefing to discuss: |  |  | Point Person:
WEEKS
|  | □ | Event goals and brand information
|  | □ | Attendee goals and engagement
|  | □ | Emergency procedures and general information
|  | □ | Booth or activities setup/managmenet
|  | Marketing |  |  | Point Person:
|  | □ | Print all marketing pieces
|  | □ | Hang banner/posters/chalking
|  | □ | Have members share and post about the event
|  | □ | [Add your own]

## 1 day
Sample Event Timeline
| Event Planners |  |  | Event Date | Event Location
| Person 1 |  |  | 00/00/0000 | Event Location
Person 2
1 |  | Check that everything is set up properly at the site |  |  | Point Person:
DAY
|  | □ | All hands on deck
|  | □ | Site plan
|  | □ | Emergency procedures in place
|  | □ | Booth or activities setup/managmenet
|  | Ensure the team members are present on the site for the event |  |  | Point Person:
|  | Set up temporary structures and booths in the event site |  |  | Point Person:
|  | Hold a final briefing/training for your event team |  |  | Point Person:
|  | □ | Event goals/brand information
|  | □ | Consumer engagement
|  | □ | Emergency procedures/general information
|  | □ | Booth or activities setup/managmenet
|  | Get a good night's sleep! |  |  | Point Person:

## Day of
Sample Event Timeline
| Event Planners |  |  | Event Date | Event Location
| Person 1 |  |  | 00/00/0000 | Event Location
Person 2
0 |  | Set up event site |  |  | Point Person:
DAYS
|  | □ | Transport all props, baskets, etc. to the venue and set up tables
|  | □ | Check that all A/V equipment works and all videos work on the venue screen
|  | □ | Decorations
|  | □ | Check in committee arrives one hour before event and sets up
|  | □ | Data entry/check out committee sets up 30 minutes prior to the event
|  | Have fun! |  |  | Point Person:
|  | □ | Document your event so you can share your efforts with everyone!
|  | After the event, clean up and store all items that can be used next year prior to leaving the venue |  |  | Point Person:

## Post-event
Sample Event Timeline
| Event Planners |  |  | Event Date | Event Location
| Person 1 |  |  | 00/00/0000 | Event Location
Person 2
1 |  | Double check that you left the venue tidy and in good condition |  |  | Point Person:
DAY
AFTER |  | □ | Advertisements
|  | □ | Temporary Structures
|  | □ | Signage
|  | □ | Booth or activities setup/managmenet
|  | Collect feedback from memebers for post-event evaluation |  |  | Point Person:
|  | Thank attendees and donors for a successful event on social media |  |  | Point Person:
1 |  | Calculate event Return on Investment and Return on Objectives |  |  | Point Person:
WEEK
AFTER
|  | Create post-event evaluation report for internal use |  |  | Point Person:
|  | □ | Update any binders/notebooks and save all pertinent info for next year's chair
|  | □ | Determine what went well and what needs to change for next year
|  | Post-event engagement |  |  | Point Person:
|  | □ | Write and send all thank you notes
|  | □ | Thank all donors, sponsors and event staff
|  | Complete the Event Summary Form |  |  | Point Person:
|  | Send in all donations to the Foundation |  |  | Point Person:
|  | □ | Ensure that all outstanding bills have been paid and balance budget in Billhighway
|  | □ | Send donations to Alpha Phi Foundation with Donation Cover Sheet |  |  | Donation Cover Sheet